## Character Estimates
Small Character Base Estimations |  |  | Medium Character Base Estimations
Category | Time Estimate (in days) | Concerncs | Category | Time Estimate (in days) | Concerncs
Design | 5 |  | Design | 5
Ai Art | 5 | Note: To get the best results its best to take a couple of days to generate correct Art | Ai Art | 5 | Note: To get the best results its best to take a couple of days to generate correct Art
Concept Art | 10 | AI-generated art can enhance the precision of concept art | Concept Art | 15 | AI-generated art can enhance the precision of concept art
3D Mockup | 5 |  | 3D Mockup | 5
Rigging | 5 |  | Rigging | 5
Animations > Dead Animations > Ability Animations > Hit Animations > Locomotion > Ability Animations > Misc Animations | 20 | If final model changes slightly, in proportions for instance, a large amount of animations have to be redone and checked again. WARNING! If the model changes more, for isntance an additional arm, a redo of the rigging and animations need happen. | Animations > Dead Animations > Ability Animations > Hit Animations > Locomotion > Ability Animations > Misc Animations | 30 | If final model changes slightly, in proportions for instance, a large amount of animations have to be redone and checked again. WARNING! If the model changes more, for isntance an additional arm, a redo of the rigging and animations need happen.
Animation BP | 15 |  | Animation BP | 17.5
Finished Model | 15 |  | Finished Model | 17.5
Animation Changes | 5 | Amount of time needed when model changes | Animation Changes | 7.5 | Amount of time needed when model changes
Prototype | 10 |  | Prototype | 17.5
Behaviour | 15 |  | Behaviour | 17.5
VFX implementation | 10 |  | VFX implementation | 10
Audio | 10 |  | Audio | 10
Polish (Tweaking / Balancing) | 15 |  | Polish (Tweaking / Balancing) | 15
Total + Safety Margin 30% | 188.5 |  | Total + Safety Margin 30% | 208
Total in Months | 6.1931 |  | Total in Months | 6.8338
Big Character Base Estimations |  |  | Huge Character Base Estimations
Category | Time Estimate (in days) | Concerncs | Category | Time Estimate (in days) | Concerncs
Design | 5 |  | Design | 15
Ai Art | 5 | Note: To get the best results its best to take a couple of days to generate correct Art | Ai Art | 5 | Note: To get the best results its best to take a couple of days to generate correct Art
Concept Art | 5 | AI-generated art can enhance the precision of concept art | Concept Art | 5 | AI-generated art can enhance the precision of concept art
3D Mockup | 5 |  | 3D Mockup | 10
Rigging | 5 |  | Rigging | 10
Animations > Dead Animations > Ability Animations > Hit Animations > Locomotion > Ability Animations > Misc Animations | 40 | If final model changes slightly, in proportions for instance, a large amount of animations have to be redone and checked again. WARNING! If the model changes more, for isntance an additional arm, a redo of the rigging and animations need happen. | Animations > Dead Animations > Ability Animations > Hit Animations > Locomotion > Ability Animations > Misc Animations | 50 | If final model changes slightly, in proportions for instance, a large amount of animations have to be redone and checked again. WARNING! If the model changes more, for isntance an additional arm, a redo of the rigging and animations need happen.
Animation BP | 20 |  | Animation BP | 20
Finished Model | 20 |  | Finished Model | 25
Animation Changes | 10 | Amount of time needed when model changes | Animation Changes | 12.5 | Amount of time needed when model changes
Prototype | 25 |  | Prototype | 40
Behaviour | 20 |  | Behaviour | 25
VFX implementation | 10 |  | VFX implementation | 20
Audio | 10 |  | Audio | 15
Polish (Tweaking / Balancing) | 15 |  | Polish (Tweaking / Balancing) | 10
Total + Safety Margin 30% | 253.5 |  | Total + Safety Margin 30% | 341.25
Total in Months | 8.3287 |  | Total in Months | 11.2117

## Characters
Characters
Name | Archetype | Group / Race / Faction | Size | Effort | Complexity | Unique Animation | Base Time in Days | Base Time in Months | Complex? | Estimation in Months | Estimation in Days
|  |  |  | Effort runs from 0 to 1 and means the amount of energy the team wants to put in the given Character. | This can be anything from VFX, Animation to Programming | Are there additional animation that need to be created next to the base ones?
Main Character | Humanoid | Faction 2 | Medium | 1 | Yes | 10 | 208 | 6.8338 | 8.884 | 11.384 | 346.4922
Npc 1 | Mythical Creatures | Faction 1 | Medium | 0.8 | No | 0 | 208 | 6.8338 | 6.8338 | 6.5605 | 199.68
Npc 2 | Supernatural Beings | Faction 2 | Medium | 0.5 | No | 0 | 208 | 6.8338 | 6.8338 | 4.1003 | 124.8
Npc 3 | Fantasy Creatures | Faction 3 | Medium | 1 | No | 0 | 208 | 6.8338 | 6.8338 | 8.2006 | 249.6
Npc 4 | Animals | Faction 4 | Medium | 1 | No | 0 | 208 | 6.8338 | 6.8338 | 8.2006 | 249.6
Npc 5 | Animals | Faction 4 | Small | 1 | No | 0 | 188.5 | 6.1931 | 6.1931 | 7.4318 | 226.2
Enemy 1 | Robots / AI | Faction 6 | Medium | 1 | No | 0 | 208 | 6.8338 | 6.8338 | 8.2006 | 249.6
Enemy 2 | Robots / AI | Faction 6 | Huge | 1 | Yes | 3 | 341.25 | 11.2117 | 14.5752 | 18.3903 | 559.7432
Enemy 3 | Mythical Creatures | Faction 1 | Medium | 1 | No | 0 | 208 | 6.8338 | 6.8338 | 8.2006 | 249.6
Enemy 4 | Fantasy Creatures | Faction 5 | Medium | 1 | No | 0 | 208 | 6.8338 | 6.8338 | 8.2006 | 249.6
Enemy 5 | Fantasy Creatures | Faction 5 | Big | 1 | Yes | 0 | 253.5 | 8.3287 | 10.8273 | 12.9928 | 395.46
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0

## Data Sheet
Time in Months
1.3 | Times for Complex Characters
0.25 | Times per Unique Animations
1.2 | Times for Non Humanoid
30.4369 | Average days in a month

## Lists
Factions | Boolean | Size | Archetype
Faction 1 | Yes | Small | Humanoid
Faction 2 | No | Medium | Animals
Faction 3 |  | Big | Mythical Creatures
Faction 4 |  | Huge | Supernatural Beings
Faction 5 |  |  | Extraterrestrial
Faction 6 |  |  | Robots / AI
- |  |  | Supernatural Entities
- |  |  | Fantasy Creatures