## Dashboard
Dashboard
Timeline
Phase

## Breakdowns
Data | [11 empty] | Phase Line | [6 empty] | Phase Date
Main Label | Second Label | Task Label | SLyL | MLyL | SLxL | Task Start | Task Duration in Quarters | TxTL | TDName | TyL | Distance | Name | Phase Start in Quarters | Phase Duraction in Quarters | Pm | Pend | Ph |  | Title | Sub-Title | Phase Description | Mile Start | Mheight
2022 | Q1 | Game Design | 0 | -20 | 1 | 1 | 1 | 2 | 12 Week(s) | 120 | 10 | Pre-Production | 1 | 2 | 2 | 3 | -30 | 10 | Pre-Alpha | (End of September 21) | We have focused on gathering information about the end user, highlighted the business contraints and found the fun of the project. This will be the colmination of the pre-production phase. | 3 | 18
| Q2 | Low level planning | 0 | -20 | 2 | 2.5 | 1 | 3.5 | 12 Week(s) | 110 |  | Development | 3 | 6 | 6 | 9 | -40 |  | Alpha | (End of March 22) | We have finished prototyping solutions that meet the needs of the end-user. We have "hopefully" discovered all problems with our design and established technical feasibility. All documentation is finished and we are ready to start development. | 5 | 18
| Q3 | Prototyping | 0 | -20 | 3 | 3 | 2 | 5 | 24 Week(s) | 100 |  | Polish | 9 | 3 | 10.5 | 12 | -30 |  | Beta | (End of March 23) | A working version of the product, based on what was learning in the alpha prototypes. We have intergrated the product into existing services, and are preparing for a transition to go live and release. | 9 | 18
| Q4 | Game Logic | 0 | -20 | 4 | 4 | 5 | 9 | 60 Week(s) | 90 |  | Maintenance | 12 | 2 | 13 | 14 | -40 |  | Release Candidate | (End of September 23) | A release version of the product, we could release now if we wanted. However, small bugs and issues may still be in the product, nothing to serious, nevertheless still things that need to be solved. | 11 | 30
2022 | Q1 | Asset Creation | 0 | -20 | 5 | 4 | 5 | 9 | 60 Week(s) | 80 | [8 empty] | Release | (End of December 23) | The final version of the product, we will continue monitoring user experiences and make adjustments here and there where needed. | 12 | 18
| Q2 | Alpha Testing | 0 | -20 | 6 | 5 | 0.34 | 5.34 | 4 Week(s) | 70
| Q3 | Beta Testing | 0 | -20 | 7 | 8 | 0.34 | 8.34 | 4 Week(s) | 60
| Q4 | Bug Fixing | 0 | -20 | 8 | 9 | 2 | 11 | 24 Week(s) | 50
2023 | Q1 | Release Preperations | 0 | -20 | 9 | 10 | 2 | 12 | 24 Week(s) | 40
| Q2 | Maintenance/Support | 0 | -20 | 10 | 12 | 2 | 14 | 24 Week(s) | 30
| Q3 |  | 0 | -20 | 11
| Q4 |  | 0 | -20 | 12
2024 | Q1 |  | 0 | -20 | 13

## Phases
Timeline |  |  | Goals
MLyL | SLyL | Gy | Gdy | Circle | Line
-2 | -1 | 8 | 7 | 0 | 6
-2 | -1 | -4 | -5 | 0 | -4
-2 | -1 | 8 | 7 | 0 | 6
-2 | -1 | -4 | -5 | 0 | -4
-2 | -1 | 8 | 7 | 0 | 6
-2 | -1
-2 | -1
-2 | -1
-2 | -1
-2 | -1
-2 | -1
-2 | -1
-2 | -1