## Weekly Report
Responsible - The person responsible for implementation. Accountable - The person who is (ultimately) responsible, authorized and approves the result. Consulted - This person is supportive of the result. Informed - Someone who is informed about decisions, progress, results achieved, etc. | Role
| Executive (CEO) | Sales Team | Project Managers | Tech Lead | Art Lead | Design Lead | Project Team Members | Administrative Support | Business Analyst | Marketing | Consultants | 3rth party suppliers
| Hiring Leadership |  |  | Hiring Members |  |  |  | Hiring Sub-Teams |  |  | Extrenal |  | Action Points
Initiate Phase Activities
Request Project Review by Sales Team | A/C | R/A | I
Create Project Proposal | C | C | R/A | C | C | C
Approve Project Proposal | R/A | C | I
Research Solutions | I |  | I | C | C | C |  |  |  |  | C
Plan Phase Activities
Create Project Charter | I | I | R/A | [7 empty] | C
Create Schedule | I | I | R/A | C | C | C |  |  |  |  | C
Create Additional Plans as Required | I | I | R/A | I | I | I |  |  |  |  | C
Execute Phase Activities
Build Deliverables | C/I | I | A | R | R | R | R |  |  |  |  | R
Create Status Report | I | I | R | C | C | C | C | I |  |  |  | R
Control Phase Activities
Perform Change Management | A | C | R | C | C | C
Close Phase Activities
Create Lessons Learned | C/I | C/I | R/A | C | C | C | C |  | I
Create Project Closure Report | I | I | R/A | [5 empty] | I
Invoice | I | I | [5 empty] | R/A
Post Phase Activities
Create Screenshots |  |  | A |  |  |  | R
Create Trailer |  |  | A |  |  |  | R
Create Blog Post | I |  |  | I | I | I |  |  |  | R/A